## Virfac
BackLog (Pending Tasks) |  |  | In Progress |  |  | Resolved (QA) |  | Validated (Pending to Merge) | Done / (Pending to Close) | Release 1.4.4 |  | Release 1.4.3.10 |  | iAM Release 1.3.2
Redmine | Priority | Branch | # | State | Time Left | # | FeedBack | # | # | # | Task Type | # | Task Type | # | Task Type
2679 | 144 Normal | 144_2679_MRS | [9 empty] | 6165 | Bug | 6034 | Bug
6086 | 144_Urgent | 144_6086_MRS | 6086 | Stand by | 12 | [6 empty] | 6203 | Bug
6158 | 143_Urgent | 143_6158_MRS | [9 empty] | 6158 | Bug
[9 empty] | 6041 |  |  | 6041 | Bug
6173 |  | 143_6173_MRS | [9 empty] | 6173 | Bug
6206 | 143_Inmediate | 143_6206_MRS | [9 empty] | 6206 | Bug
6213 | iAM 1.4 | master_6046_MRS | 6123 | Working
6214 | iAM 1.4 | master_6046_MRS | 6214 | Working
6211 | iAM 1.4 | master_6211_MRS |  |  |  | 6211
6160 | iAM 1.4 | master_MatMngr_6160_MRS |  |  |  | 6160
6151 | iAM Urgent | 13_6151_MRS | [11 empty] | 6151 | Bug
6146 | iAM 1.4 | master_6046_MRS |  |  |  | 6146
6125 | iAM 1.4 | master_6046_MRS |  |  |  | 6125
6127 | iAM 1.4 | master_6046_MRS |  |  |  | 6127
6126 | iAM 1.4 | master_6046_MRS |  |  |  | 6126
6124 | iAM 1.4 | master_6046_MRS |  |  |  | 6124
6123 | iAM 1.4 | master_6046_MRS |  |  |  | 6123
6046 | iAM 1.4 | master_6046_MRS |  |  |  | 6046
6116 | iAM 1.4 | master_6116_MRS |  |  |  | 6116
6118 | iAM 1.4 | master_6046_MRS |  | Stand by |  | 6118 | #5
Working
Stand by

## History Released
Release 1.4.3.9 |  | Release 1.4.3.10
# | Branch to Delete | # | Task Type
5930 | Bug | 6165 | Bug
5875 | Bug | 6203 | Bug
5887 | Feature | 6158 | Bug
5738 | Bug | 6041 | Bug
5963 | Feature | 6173 | Bug
6051 | Bug | 6206 | Bug
5454 | Feature
6031 | Bug
5736 | Bug
5883 | Bug
6041 | 143_5885_MRS Bug
5885 #8 | 143_5885_MRS Feature

## Hours
Last week hours: | 1.25 | Enter | Exit | Enter | Exit | Lunch | Total | ACTIVE | Hours | Difference
Monday | 7.75 | 8:50 | 17:35 |  |  | 1:00 | 7:45 | YES | 8 | -0.25
Tusday | 8 | 8:50 | 17:50 |  |  | 1:00 | 8:00 | YES | 8 | 0
Wednesday | 0 | 9:00 | 17:00 |  |  | 1:00 | 0:00 |  | 0 | 0
Thursday | 0 | 8:15 | 17:30 |  |  | 1:00 | 0:00 |  | 0 | 0
Friday | 0 | 9:00 | 17:00 |  |  | 1:00 | 0:00 |  | 0 | 0
Total | 17 | [8 empty] | -0.25
Objetive | 16 | [7 empty] | 16
End week hours: | 1

## 1.4.3
# | Subject | Author | Comment | Time | Priority | Notes
2726 | Change selector | Elise | Selectors | Normal | 5_S | 2726_15. | RM #2726. Adding Conditions: VirfacLib.HeatTreatment.
2632 | Reference temperature for thermal expansion not clear | Elise | Materials | Short | 1_U
994 | .VFCM files should be compatible between US and SI unit systems | Elise | Units | Normal | 2_H
1816 | Disconnect weld trajectory from CAD Edge | Michel | WDesigner/Scheduler | Long | 2_H
1904 | Link cooling stages to welding stages (multipass welding and cladding) | Elise | WDesigner | Short | 2_H
2707 | [Scheduler] Improve Welding Scheduler User Interface | Manuel/Elise | WScheduler | Normal | 2_H
626 | Testing APT code | Michel | WeldBeads | Normal | 3_N
756 | Seeing weld beads parameters after creation | Elise | WeldBeads | Long | 3_N
815 | JSOL369: Rectangular selection of surface and edges | Shin | AgentSelector | Normal | 3_N
929 | Von Mises equivalent values in field viewer for stress and strain | Adhish | FieldViewer | Long? | 3_N
932 | Intersection between a face and a block: sphere or cylinder | Elise | BoundaryConditions | Long? | 3_N
981 | Selecting faces from already created BC | Benjamin | CAD tools | Normal | 3_N
1051 | JSOL440 : Different color of front and back surface | Shin | Agents | Normal | 3_N | Discuss
1067 | Welding designer: starting/ending heat source before/after trajectory edge | Elise | HeatSource? | Long | 3_N
1280 | Max number of points in Materials TXT files | Laurent | SolverBMorfeo | Short | 3_N
1291 | Weld beads manager modification | Elise | WeldBeads | Normal | 3_N
1303 | FSW UI evol (Welding speed, with Xavier) | Michel | FSW, welding speed? | ? | 3_N | Xavier
1313 | FSW UI evolution (Canvas) | Michel | FSW (canvas) | Normal | 3_N
1409 | Offer the user to modify by hand the time step | Elise | SolverSettings? | Normal | 3_N
1467 | 1.4.0.3 display selected CAD entities in creators | Elise | AM | Normal | 3_N
1504 | FSW tools creator: allow negative shoulder angle | Elise | FSW | Long? | 3_N
1526 | FSW heat source | Elise | HeatSource | Short? | 3_N
1879 | Contact condition on several assemblies: automatically change the rendering of assemblies | Elise | BoundaryConditions | Normal | 3_N
1894 | Export mesh after update vertex position | Elise | SolverSettings | Short | 3_N | Joe
1918 | AM: add transparency to the yellow part | Elise | AM | Short | 3_N
1939 | JSOL639 Delete Visible and Unreferenced CAD Models | Shin | CAD tools | Short | 3_N
1953 | cladding => apply to all for start point, end point, reverse direction | Elise | Wdesigner | Normal | 3_N
2019 | BC with intersection: check intsersection | Xavier | Tool Room | Normal | 3_N | In Progress
2039 | mechanical activation by block | Elise | WDesigner | Normal | 3_N
2061 | Cladding: add offset parameter | Elise | WeldBeads | Normal | 3_N
2104 | scheduler: decrease the number of arrow or change arrow size for *.pos file | Elise | Inherent Strain | Normal | 3_N
2123 | Scheduler: allow multi-selection | Elise | WScheduler | Long | 3_N
2124 | Scheduler: add a view trajectory button at the database selection | Elise | WScheduler | Short | 3_N
2162 | Scheduler: Merge welding stages | Elise | WScheduler | Long? | 3_N
2276 | 1.4.2 AM LG modeling conditions: change apply to all button | Elise | AM | Short | 3_N
2285 | AM: Dissociate modeling conditions from layers | Elise | AM | Normal | 3_N | #2276
2333 | Support creation | Michel | CAD tools | Normal | 3_N | VTK Mesh
2361 | Scheduler: link the name of the patch with the name of the welding stage | Elise | WScheduler | VeryShort | 3_N
2434 | Scroll bar and windows size improvement | Elise | Operations/All Virfac | Normal/Long | 3_N
2491 | 1.4.2 AM Assembly: imprint does not work | Elise | AM | * | 3_N | To be checked, could be solved
2498 | Reset the window size when changing of CAD tool | Maud | AM | VeryShort | 3_N
2500 | AM: no error for wrong inherent strains values | Maud | AM | Short | 3_N
2510 | CAD tool "create am support": check volumes | Elise | CAD tools | Normal | 3_N
2531 | AM: Error when slicing is interrupted | Maud | AM | VeryShort | 3_N
2589 | Phases and Transformations manager: let the user decide on the width of the left area | Elise | Materials | Short | 3_N
2625 | BC point selection: switch back the rendering of the assembly to solid | Elise | ToolRoom | Short/Normal | 3_N
2652 | Morfeo SolverBridge: group bodies per materials | Elise | SolverBridge | Short/Normal | 3_N
2653 | deactivate parts manager when no cad model are available | Elise | Geometry/Parts | Normal | 3_N
2660 | [Parts] Assembly Creator: Merge several volumes in one with only one CAD Model | Manuel/Elise | Parts | Normal | 3_N
2665 | [Materials] Use copy/paste tool to load (import) datas from Excel | Manuel/Michel | Materials | Normal | 3_N | Xavier
2679 | [Selectors] Resynchronization of faces for all Virfac | Manuel/Michel | Selectors | Normal | 3_N
2693 | Make FSW Tools Manager accessible outside the assembly | Adhish | FSW | Short | 3_N | View Changes
2710 | Designer: Merge welding stages OR Scheduler: Merge pos file | Elise | WDesigner/Scheduler | Normal | 5_S | RM #2710_1
2712 | keep materials of weld bead | Elise | Parts | Normal | 3_N
2724 | Intermittent welding stages in Welding Designer analysis | Elise | WDesigner | Normal | 3_N
2725 | Duplicate welding stages in welding designer | Elise | WDesigner | Normal | 3_N
2727 | Selection inside the volume using a slice | Elise | Selectors | Normal | 3_N
1972 | 1.4.1.1: AM Local global - progress bar with no CAD slicing | Maud | AM | Short | 4_L
2099 | Scheduler: missing information on synchronized weld beads | Elise | WScheduler | Short | 4_L
2733 | Machining LS: import sheets by default | Elise | Machining | ??? | 4_L
2735 | increment names once the object is created | Elise | WeldingDesign | Short | 4_L
1806 | Local-Global method to be developped for multi-pass simulation (Scheduler) | Elise | Inherent Strain | Long | 0_F | 1806.#19
2127 | Synchronize with weld beads: synchronize only missing welding stages | Elise | Wdes./Sche./WeldBeads | Normal | 6_C | Merged
2376 | Scheduler: Name of the inherent strains may be hidden if too long | Maud | Inherent Strain | Short | 5_S
2385 | CLAD picture | Michel | Clad | Short | 0_F | View Changes, Merged into master
2398 | Scheduler: check the files used for an existing inherent strain database | Maud | Inherent Strain | Short | 5_S | To Merge waiting for 1806
2678 | [Selectors] Resynchronization of edges for all Virfac | Manuel/Michel | Selectors | Long | 5_S | Elise / Konno - Merged
2706 | [Inherent Strain] Refactor Inherent Strain Manager | Manuel/Elise | Inherent Strain | Long | 5_S | To Merge waiting for 1806
1731 | 1.4.0.9 units are not checked when importing inherent strains | Elise | Inherent Strain | Long | 6_C | 1.4.2
2353 | MESO: copy button | Michel | Meso | Short | 6_C | View Changes
2664 | [Materials] Use the .txt files only to load (import) datas | Manuel/Michel | Materials | Short | 6_C | Adhish
BUGS
BRANCHES to merge
143_5885_MRS
143_5963_MRS
143_5736_MRS
143_5454_MRS
143_6031_MRS
BRANCHES to delete
143_5930_MRS
143_5875_MRS
143_5887_MRS
143_5738_MRS
#2726 | FeedBacks
#23 | I found some bugs during translation. No.1 : Virfac crash at Merge Adjacent Volumes of CAD Tools Open "Merge Adjacent Volumes" window Select CAD model Select CAD Volume 'System.StackOverflowException' occurred and Virfac crashed. Note : This issue does not reproduced at "master" branch. | Linh
#24 | Comment #12 not solved yet. 'C': Selection mode back to "CAD model" however selector window still opend. Esc : Sometimes close selector window. Sometimes clear selected items. I think some old short-cut specifications is not matched at new selector window. Please confirm Virfac.xaml.cs(Line:158) and comment out unnecessary code or add new short-cut specifications. | #34 Shortcuts | 5_S
#25 | No.3: Selctor window title When opened selector window, user cannot confirm selection target feature. DisplayName property of AgentSelectorBaseVM is apply to selector window title. However almost selector does not set DisplayName property. This problem already written comment#10. Please reply to Comment #10. | #35 Name | we decided to put the Name in the header only to save space. It's binding to the DisplayName property but shouldn't be changing by the user, only in the selector that call it.
#26 | No.4: Closing selector window After close selector window, top window is last opened window. It should be selector owner window. Open operation window Open CAD tools window Open selector window of operation window close selector Top window is CAD tools! (Also #10) A moment animation of CAD and Part icon. however other icon (e.g.Mesh, Run) is not animation. |  | 5_S
#27 | No.5 : Does not lock scene when List box selection changed List box of selector window can select multi items. When 100 or more items exist, all item selection is very slowly because update scene many times. Please add scene lock. | #37 Scene.lock | 5_S
#28 | No.6:Cannot re-press "Remove selected" button Press "Remove selected" button, the listbox selected item is none. Other manager window, automatically selected next item after remove item. | 1.- This selector is not a manager, it is a tool. So the behaviour is diferent to the managers in Virfac. 2.- This 'second' selection is only a helper.
#29 | No.7:Invalid conditon string Machining.Resources.Strings.ERR_ContainVolumes is incorrect. "Must contains at least one volume. The model should only involve faces." Please confirm MachiningPassVM.cs(line:686). This selector can not select volume. | The model should only involve faces, cannot conatin any volume. | 5_S
#30 | No.8 : Welding Path selector Please confirm following image. | The selected path CAD Edges cannot be internal. Please select only CAD Edges lying on the boundary of a CAD model. | 5_S
#31 | No.9 : Same condition string at different selector Part.Resources.Strings.WARN_CadVolumeAttributes The volume attribute should be correct. This message using at 2 selectors. However the selector allow attribute is different. Please compar line: 1842 and 1907 of AssemblyLocalFSWCreatorVM.cs. I think this message is not easy to user. Should use different messages for each selector. | WARN_CadVolumeContactLayer Please select a contact layer volume. Please select a backing plate volume. | 5_S
#32 | No.10 : Miss spell GeometryTools.Resources.Strings.WARN_IncorrectCadEdge Selected CAD edge msut belong to a valid CAD model. | Linh
#33 | *********************
#34 | short-cut "C" does not work properly. When using "C", behavior of the selector is disconnected from the selector box | #24 Shortcuts | 5_s
#35 | What about the name of the selector? (from spec: "At the top of the window, two lines of non-editable strings: 1. Name of selection (e.g. “Select welding path”, “Select boundary condition domain”, …) 2. Type of selection expected (e.g. “Type: Multiple CAD edges”, “Type: Single CAD face”, …)" ) | #25 Name | I decided to put the Name in the header only to save space. It's binding to the DisplayName property but shouldn't be changing by the user, only in the selector that call it.
#36 | SELECT SINGLE PART (WORKPIECE): - A part may only be connected to a single CAD model > "Please select a single CAD model" ? - CAD Model > CAD model (be consistent in the use of caps) - CAD model cannot be connected to another part! > (remove "!") "CAD model cannot be already connected to another part." - CAD model cannot be used in more that one assembly > I think this one has nothing to do here. - Please select a solid CAD model: to be moved 2nd line. to have: - Please select a single CAD model - Please select a solid CAD model - CAD model cannot be already connected to another part |  | 5_S
#37 | Edges highlight takes along time. I think we should think of a more optimize way to highlight parts. (either optimize the management of edges, or forget about edges and change color of the selected part, or any other idea?) | #27 Scene.lock | 5_S
#38 | SELECT MULTI PARTS: Same comments as before, + "A part may only be connected to a single CAD model" > I think this one has nothing to do here. | #36 | 5_S
#39 | when selecting a part that is not correct, the criterion that is not respected is isolated with a new color, and other criteria are hidden. I think that it is good to change the color of the one that is not respected, but you should not hide the other |  | 5_S
#40 | WELD BEADS MANAGER - Type "GENERATED". Edge selection "Selection is limited to a single edge" > I think we should keep consistency in all selectors, and all of them limited to a certain number of items to select should start with : "Please select a single [or only X (if X>1)] CAD edge[s (if X>1)][or face or model or ...] "The selected item should be belong to the working assembly" > "The selected item should belong to the current assembly" "All the selected items should be belong to the working assembly part" > ? isn't it the same as the previous line? |  | 5_S
#41 | Add information: number of selected entities Maybe in the right area, above or below the buttons "Clear selection", … | New Feature
#42 | If only one single CAD entity can be selected, then hide or grey out “All”, “Same type” and “Same component part”. | SingleElementConstraint = true, | 5_S | Identify the selectors
#43 | If only one single CAD entity can be selected, then selected a second entity should replace the first selected entity. (behavior similar to previous padlock behavior when the user select several entities without pressing ctrl) | Not was in all | 5_S | Identify the selectors
#44 | File 1.png View added Quote Edit Delete In Machining module -> Operation Manager -> CAD geometry selector The two lines highlighted in yellow are redundant. You might keep the second. The word underlined in red might be a mistake. And for the the blue color, I think it can't be a volume and a open sheet. |  | 5_S
#45 | File 1.png View added Quote Edit Delete Machining/Heat treatment (I think in all modules) -> Mesh Manager -> CAD Based Meshing Controls -> CAD Face/CAD Edge Could add "Select at least one face/edge" next to the button "ok" when this one is blocked (the first time you open the selector) ? | Please select at least one object to activate the buttons. | 5_S
#46 | File 1.png View added File NewProject.7z added Quote Edit Delete Mesh Manager -> CAD Based Meshing Controls -> CAD Edge Selector The selector behavior is really strange. When I select two edges the selector is blocked and says "Select only one..." Perfect! but when I deselect the second by a double-click the selector is still blocked. And when after that I select a third it works. So I think the two first edges have been deselect but they're still "colored" on the GUI. | *Releated with #43. | 5_S
#47 | CAD TOOLS (Linh?) The "undo" button changes from activated to grey out when we opening/closing the selector. I think it should still be active. | Linh
#48 | Boundary conditions « This condition does not apply to sheet CAD models »  not useful “All geometric entities in your selection must be belong to an assembly. Please select only entities that belong to assemblies”  “Please select only entities that belong to an assembly” |  | 5_S
#49 | [CAD TOOLS] (Linh?) Distance between points Select two nodes. Click OK Open the selection Select one among the two available “Remove selected”: Exception caught: Fatal error Exception has been thrown by the target of an invocation. See the log file for further details. The log file can be opened either through the Virfac® main menu or by clicking on "OK" below . [Details] 1. Collection was modified; enumeration operation may not execute. |  | 5_S
#50 | Welding designer – welding pass “All selected item must be belong to the working assembly part”  “Please select only entities that belong to an assembly” “The selected path CAD Edge cannot be internal. Please select only CAD edge lying on the boundary of a CAD model”  “Please do not select internal CAD edge”. Be careful with redmine2710, “Please select connected CAD edges” Distance between nodes “Selected CAD nodes mstu Parasolid ones”  “Selected CAD nodes must belong to a Parasolid CAD model”. CAD topology: “can not” > “cannot” Can you try to harmonize the texts? in the cad tools, the sentences are a bit too complicated. “Please select only …” (Please select only discrete CAD models, Please select only Parasolid CAD models, Please select only sheet bodies, …) Or, if you want to use passive form, “Only … can be selected”. For instance, “Only Parasolid CAD models can be selected”. seems better |  | 5_S
#51 | *******************************
#52 | If a mesh is selected instead of a CAD model in a selector in which only Parasolid CAD models are allowed, then the mesh stays in red even if we are selecting something else or if we cleared the selection. If the wrong type is selected, it should not be red either at all, or from the moment we click on another item. |  | 5_S
#53 | I don't think that informative strings on selection such as "Please select a single CAD point/a Parasolid CAD, ..." should be visible outside of the selector (before this type of selector, this was the only place where we had this information. Now we should only see this information inside the selector) | new Feature
#54 | CAD TOOL EXTRACT CAD VOLUMES AS SOLID MODELS. Select volumes > right click = "Reset view" and "Show/hide edge diameters". Click OK to end the selection. Enter the selector again > right click = "Select all CAD volumes", "Select all CAD volumes (same type)", "Reset view" and "Show/hide edge diameters". "Select all CAD volumes", "Select all CAD volumes (same type)" should not appear. Same thing for CAD faces selector type. |  | 5_S
#55 | CAD TOOLS - EXTRACTION - Extract geometry from cad model by extrusion - Select CAD edge: "sequence contains no element" in the cad tool, + "wrong item selection" in the selector, which does not work. | Linh
#56 | CAD TOOLS - EXTRACTION - Extract mid-surfaces between CAD faces: "Select CAD faces right": select items. "OK". Open selector: selector is empty. | Linh
#57
#58
#59
#60
#61 | Michel's request????????????

## 1.4.2.Patch
# | Subject | Author | Comment | Time | Priority | Notes
2583 | [FSW] Allow CAD Based tools with negative Shoulder angle (alpha) | Atsushi/Michel | FSW | Normal/Long | 6_Closed
1793 | [Virfac 1.4 Crack] propagation advance parameter | Pierre | Crack | VeryShort | 6_Closed |  | View (CadModelsManager)
1850 | [Welding Designer] - Multi-pass welding: Export plasticStrain after each pass | Elise | WDesigner | Short | 6_Closed | Joe
1871 | Phases manager (strong coupling): save selected file | Elise | Sparameters | Normal | 6_Closed
2029 | Let the cad models sorted by date of creation | Elise | Cad Models Manager | Short | 6_Closed | Xavier(Depency Property)
2091 | Scheduler: automatically create a patch when a welding stage is created | Elise | WScheduler | VeryShort | 6_Closed
2129 | AM - Zmin for the new supports creation tool | Maud | CAD tools | Normal | 6_Closed
2221 | Virfac AM: no special faces for support with a discrete model | Maud | AM | Normal | 6_Closed | Adhish
2262 | Immersion quenching - UI | Ahdish | HT | Normal | 6_Closed | Adhish
2307 | Designer: Export plastic strain before relaxation | Maud | Relaxation | ??? | 6_Closed | Joe | View (SolverSettings)
2311 | Scheduler: Error message not very clear for loading plastic strain | Maud | Inherent Strain | VeryShort | 6_Closed
2337 | Generate weld beads: "use filler material" should be checked by default | Elise | WeldBeads | VeryShort | 6_Closed
2395 | scheduler: confirmation message when closing inherent strain creator | Elise | Inherent Strain | Short | 6_Closed
2404 | Welding designer "pass index" not correct | Elise | WeldBeads | VeryShort | 6_Closed
2489 | 1.4.2 fsw create local geom. missing error message if padlock is closed instead of create | Elise | FSW (parts) | Normal | 6_Closed
2490 | 1.4.2 Create an AM CAD support: does not work if only 1 element in one direction | Elise | AM | ??? | 6_Closed
BUGS
2539 | Actors crack | Closed.
2457 | Points Mesh | Closed.
1446 | HT, When delete the assembly, delete all the objects binding to this assembly en HT stages | Closed.
2509 | Should be a new Feature | Closed.
1731 | Units | Resolved.
2585 |  | Closed.
2670 |  | Resolved.
2668 |  | Resolved.

## 1.4.2
# | Subject | Author | Comment | Time | Priority | Related
1944 | [Virfac AM Meso] User interface | Adhish | ALM | Long
1467 | 1.4.0.3 display selected CAD entities in creators | Elise | ALM | Normal
1972 | 1.4.1.1: AM Local global - progress bar with no CAD slicing | Maud | ALM | Short
1918 | AM: add transparency to the yellow part | Elise | ALM | Short
932 | Intersection between a face and a block: sphere or cylinder | Elise | BoundaryConditions | Long?
1879 | Contact condition on several assemblies: automatically change the rendering of assemblies | Elise | BoundaryConditions | Normal
2029 | Let the cad models sorted by date of creation | Elise | Cad Models Manager | Short
981 | Selecting faces from already created BC | Benjamin | CAD tools | Normal
2019 | BC with intersection: check intsersection | Xavier | CAD tools | Short
1939 | JSOL639 Delete Visible and Unreferenced CAD Models | Shin | CAD tools | Short
929 | Von Mises equivalent values in field viewer for stress and strain | Adhish | FieldViewer | Long?
1504 | FSW tools creator: allow negative shoulder angle | Elise | FSW | Long?
1313 | FSW UI evolution (Canvas) | Michel | FSW (canvas) | Normal
1303 | FSW UI evol (Welding speed, with Xavier) | Michel | FSW, welding speed? | ?
1526 | FSW heat source | Elise | HeatSource | Short?
1067 | Welding designer: starting/ending heat source before/after trajectory edge | Elise | HeatSource? | Long
1806 | Local-Global method to be developped for multi-pass simulation (Scheduler) | Elise | Inherent Strain | Long
1731 | 1.4.0.9 units are not checked when importing inherent strains | Elise | Inherent Strain | Long
1552 | [Virfac] JmatPro import :general steel | Elise | JMatPro | Normal
1118 | CAD View & Handling | Emmanuel | Scene | Normal
1280 | Max number of points in Materials TXT files | Laurent | SolverBMorfeo | Short
1894 | Export mesh after update vertex position | Elise | SolverSettings | Short
1409 | Offer the user to modify by hand the time step | Elise | SolverSettings? | Normal
1871 | Phases manager (strong coupling): save selected file | Elise | Sparameters | Normal |  | #756
994 | .VFCM files should be compatible between US and SI unit systems | Elise | Units | Normal
2039 | mechanical activation by block | Elise | WDesigner | Normal
1953 | cladding => apply to all for start point, end point, reverse direction | Elise | Wdesigner | Normal
1850 | [Welding Designer] - Multi-pass welding: Export plasticStrain after each pass | Elise | WDesigner | Normal
1904 | Link cooling stages to welding stages (multipass welding and cladding) | Elise | WDesigner | Short |  | #1816
1816 | Disconnect weld trajectory from CAD Edge | Michel | WDesigner/Scheduler | Long
2061 | Cladding: add offset parameter | Elise | WeldBeads | Normal
756 | Seeing weld beads parameters after creation | Elise | WeldBeads | Long
1291 | Weld beads manager modification | Elise | WeldBeads | Normal
1074 | 1.3.1 welding designer, flat weld bead creation: the user should know which side is "a" and which is "b" | Elise | WeldBeads | Normal
663 | ‘Total Volume of Weld Material’ and ‘Mass of Weld Bead’ Information should be Available. | Amod | WeldBeads | Normal
1128 | Element Activation in Scheduler: display the cylinder created with the radius | Elise | WeldingScheduler | Short

## 1.4.1
# | Subject | Author | Comment | Time
1806 | Local-Global method to be developped for multi-pass simulation (Scheduler) | Elise | Inherent Strain | Long
1780 | FSW; Assigning materials with different macro-buttons | Elise | DONE
1731 | 1.4.0.9 units are not checked when importing inherent strains | Elise | Inherent Strain | Long
1730 | Scheduler: check for consistency of the patch size | Elise | W_Scheduler | Short
1635 | Virfac Welding: Imported weld beads should support mesh imported parts | Elise | WeldBeads | Normal
1552 | [Virfac] JmatPro import :general steel | Elise | JMatPro | Normal
1526 | FSW heat source | Elise | HeatSource | Short?
1504 | FSW tools creator: allow negative shoulder angle | Elise | FSW | Long?
1467 | 1.4.0.3 display selected CAD entities in creators | Elise | ALM | Normal
1445 | morfeo - 3Global model on hex elements : non physical displacement | Elise | SolverSettings | Short
1409 | Offer the user to modify by hand the time step | Elise | SolverSettings? | Normal
1313 | FSW UI evolution | Michel | FSW (canvas) | Normal
1303 | FSW UI evol | Michel | FSW, welding speed? | ?
1291 | Weld beads manager modification | Elise | WeldBeads | Normal
1280 | Max number of points in Materials TXT files | Laurent | SolverBMorfeo | Short
1128 | Element Activation in Scheduler: display the cylinder created with the radius | Elise | WeldingScheduler | Short
1118 | CAD View & Handling | Emmanuel | ? | ?
1074 | 1.3.1 welding designer, flat weld bead creation: the user should know which side is "a" and which is "b" | Elise | WeldBeads | Normal
1067 | Welding designer: starting/ending heat source before/after trajectory edge | Elise | HeatSource? | Long
994 | .VFCM files should be compatible between US and SI unit systems | Elise | Units | Normal
981 | Selecting faces from already created BC | Benjamin | CAD tools | Normal
932 | Intersection between a face and a block: sphere or cylinder | Elise | BoundaryConditions | Long?
931 | Select CAD nodes for boundary conditions | Elise | BoundaryConditions | Normal
929 | Von Mises equivalent values in field viewer for stress and strain | Adhish | FieldViewer | Long?